## System Test
Test Plan
See below for Test Coordinators and Team Assignments
TEST SCRIPT | EXPECTED RESULTS | DATA / SYSTEM CONDITIONS | ON LINE TRANSACTIONS | DATE PERFORMED | TESTER | ACTUAL RESULTS | COMMENTS
User Acceptance
Home Page
1. Test New User Login capabilities | Site prompts user for ID and password and sends email to confirm login credentials | Test with 10+ users to confirm all condtions |  | 2016-07-31 |  | Tests performed as expected however reset password function did not sent email
2. Test Entering a New Success Story | Link on home page takes user to screen where they can enter a success story. Screen checks user login credentials to confirm ability to access screen. New success story appears on the list of other success stories | Test with different user credentials to ensure system checks on ability to access pages |  | 2016-07-31
3. Test links to Facebook and other social media sites | Clicking link takes user to Facebook page | Test to see if link goes to new window |  | 2016-07-31 |  | Link worked as expected
4. Test Links to other organizations | Clicking link takes user to other web sites | Test to see if link goes to new window |  | 2016-07-31 |  | Link took user from home page to other site (new window did not pop open) | Failed
Integration Test
1. Get fiels from partner FTP server | FTP site allows secure download | Load multiple files from FTP |  | 2016-08-24 |  | Files successfully downloaded
2. Test ETL scripts and loading into database | ETL scripts transforms flat file data and maps into MS SQL SVR format | Test scripts for missing data and file formats |  | 2016-08-24 |  | ETL scripts incorrectly mapped data into partner tables
3. Test error handling on data load | Review error logs to determine if any data was ommitted or tagged as unloadable | Review error logs and error reporting with support users |  | 2016-08-24 |  | Error logs worked as expected
4. Review data from web pages | Review search results, queries or other reports within the site to determine if data loaded correctly |  |  | 2016-08-24 |  | Queries / search results performed as expected
System Test
Security Test
1. Test Ingenium ID's for access to menus and screens. | User ID / Passwords provide the correct access for each profile. Users are presented with the required menu options. | Test security for the Sales Annex and regional sales office users. |  | 2016-08-31 |  | ID's were successfully tested for the Call Center, Underwriting, New Business, Sales, Commissions, Finance, and Data Center Operators. Menu options verified to display proper selections for each user profile. Sign-on and security access were successful for Sales Annex and regional offices.
2. Test Ingenium ID's for update capabilities - add, delete, etc. | User ID / Passwords provide the correct update capabilities for each profile. Users are permitted to add/delete/update bases on their user profiles. | Logon using all key security profiles Test auto signoff after 30 minutes Test that user can only be signed on to one session at a time |  | 2016-08-31 |  | ID's displayed the expected secuirty access rights. Auto signoff occurred as expected after 30 minutes Verified that one user can be signed on to one session at a time. | Delete capabilites incorrectly appear on selected "List" screens. Need to modify Ingenium to remove for unauthorized users.
Backup / Restore Testing
1. Test the backup process for the Ingenium model office region. | Backup processing completes without an errors and in the expected time frame. | Use Espresso to schedule monthly backups. Use Net Backup for daily restores. |  | 2016-08-31 |  | Succesfully tested all backup processes for the model office region using NetBackup. Verified that monthly backups completed as scheduled through Espresso.
2. Test the restore process for the Ingenium model office region. | The restore process for Ingenium completes as expected and all system features are operational. | Test after batch completes. After one day's work, restore to previous day. |  | 2016-08-31 |  | Successfully restored all model office code.
3. Test backup of the Exstream production environment. | Backup processing completes without an errors and in the expected time frame. | Use Espresso to schedule backups. |  | 2016-08-31 |  | Successfully backed up the Exstream production region.
4. Test restore of the Exstream production environment. | The restore of the Exstream files are successfully restored and are fully operational. |  |  | 2016-08-31 |  | Successfully restored the Exstream production region.
Print Operations
1. Test printing of contracts, forms, letters and bills after an Ingenium batch cycle and subsequent Exstream batch cycle. | All key documents form the Exstream batch cycle print as expected. Output is printed from the correct paper tray and prints in the prescribed sequence. | Test from Model Office region |  | 8/15 - 8/31 |  | All key documents printed as expected from the correct paper tray.
2. Test printing of checks (via Exstream) after an Ingenium batch cycle. | Checks print as expected to production check printer. All print security features are tested successfully. | Test from Model Office region |  | 8/15 - 8/31 |  | Checks printed sucessfully using security features from laserjet printer.
3. Test printing of Ingenium reports after a batch cycle. | Ingenium batch reports print as expected to prodcution printers. | Test from Model Office region |  | 8/15 - 8/31 |  | Ingenium batch reports printed as expected from Printer 1.
4. Test Print 'Q' Manager for all printing jobs. | Print 'Q' Manager allows operators to manage print jobs from their console. Print jobs can be managed for failure scenarios, printer problems and other key operational scenarios. |  |  | 8/15 - 8/31 |  | All print jobs successfully monitored from Print 'Q' Manager. Was able to redirect print jobs based on printer failures (i.e., ink cartridge problems, empty paper tray)
5. Test the printing performance for high volume output (e.g., checks, letters, etc.) | Printing operations produce output in expected time frames with minimal delays. |  |  | 8/15 - 8/31 |  | Printer output printed at expected speed with no delay.
Failure Testing
1. Test Hardware failure for SunFire and Compaq servers. | Sever failure(s) are successfully managed with pre-defined remediation procedures: soft shutdown of hardware, use of system redundancy features, restart / recovery of hardware components, etc. All software components are not damaged or adversely affected by hardware failures. | Test redundant power supply, network connection and Host Bus Adapters |  | 2016-08-31 |  | Removal of fan tray and power module had no measurable effect on performance of SunFire server. In addition, removal of network interface card did not affect the operation of key applications (CICS, Oracle). | Test SunFire hardware redundancy (fan trays, power, supply), and Network Interface cards
2. Test power failure effects on the following: - Exstream batch processing - Ingenium batch processing - Espresso processing - Print operations - Backups and restores | After power failures are effected, emergency systems (e.g., battery systems) kick-in, system alerts are triggered and shutdown procedures are effected. Upon resumption of power, error logs/reports are reviewed and interrupted processes are restarted and complete as expected. | Trip circuit breaker(s), where applicable, to simulate power failure For Espresso, test failure of the Sun Ultra 60 and servers with agents. |  | 2016-08-31 |  | Power failure was affected and resulted in the following: Espresso server shutdown while server4 copfiles.bat script was running. No effect - job finished successfully. Storage arrange powered down successfully. Chico on SunFire gracefully forced shutdown of all applications, including Oracle, CICS, cybAgent, and sfs server. | Facilities to check: Power failure via panel cutoff, Espresso server and agent failure.
3. Test CICS failure and recovery procedures for Ingenium online access. | CICS is interrupted and shut down and restart procedures successfully resumes online access. | Create "hanging" condition to simulate CICS failure |  | 2016-08-31 |  | Removed /ing/ut/server/binbatch and bin rdirectories while CICS was running. No measurable effect was detected. | Front-end restart (Websphere)
4. Test Oracle failure (while CICS is running). | Oracle failure is managed by predefined remediation procedures. Interrupted Ingenium processes are managed with minimal problems and all Ingenium components are | Simulate disconnect from Oracle to Ingenium and other key systems. |  | 2002-12-21 |  | Added tablespace (containing a signle test data file) to the IDEV Oracle instance on Chico. Created backup of of the file and then added more rows to the table. Deleted the datafile using the "remove" command and verified that the status was "bad". Restored the datafile from backup and executed the "recover tablespace" command. Oracel reported media recovery was complete and verified that the database was recovered right up until the point of failure. | Oracle database failure and restore; data destruction and restore
5. Kill / shut down CICS. | After the "kill -9" command has been issued, CICS is successfully restarted. | Issue the Kill -9 command |  | 2002-12-21 |  | CICS applictions were killed manually. Full restart of CICS was initiated without any problems. | CICS application hung or killed; restart process
6. Test systems alerts | System failures trigger automated alerts via expected methods: email, paging, phone. | Have pagers, cells phones, etc. available |  | 2002-12-21 |  | All failure tests generated email to G. Gagnon. All tests generated alerts on "Big Brother". | Notification via "Big Brother" monitoring tool, and individual job notification from Espresso.
Test Data Required
Accounting Transactions

## Production Test (hidden)
Production Test
Test Plan Objectives: | See below
TEST SCRIPT | EXPECTED RESULTS | DATA REPORTS REQUIRED | ON LINE TRANSACTIONS | DATE PERFORMED | TESTER | ACTUAL RESULTS | COMMENTS
Performance Testing
1. Test response time for Ingenium on-line use and processing | System response time meets expected standards - 2 to 3 seconds. | Have 40+ concurrent users involved in testing.
2. Test response time for multiple applications open at the same time. | System response meets expected standards - 2 to 3 seconds - when all major systems (Ingenium, Bull, Sales Illustration, Tele-Marketing, Microsoft Outlook, etc.) are opened/running at the same time. | Have 40+ concurrent users involved in testing.
3. Test Sales Illustration and Tele-Marketing performance. | System response and processing meets expected standards. | Test response times for the Sales Annex and regional sales offices
Batch Testing
1. Test Ingenium batch cycle. | All Ingenium jobs execute as expected; interface files are generated and transmitted to service providers, banks, Oracle A/p and G/L, and Exstream; Ingenium reports are produced successfully. | Run batch from Production region
2. Test Exstream batch processing | All output - forms, bills, letters, policy pages and checks - are produced successfully. | Run batch from Production region
3. Test all consolidated reporting processes. | The daily and monthly sales report accurately reflects data from both the Bull system and Ingenium. Bi-weekly emails are created and sent with combined Ingenium and Bull pending data.
Security Testing
1. Test Ingenium ID's for access to menus and screens. | User ID / Passwords provide the correct access for each profile. Users are presented with the required menu options. | Test security for the Sales Annex and regional sales office users.
2. Test Ingenium ID's for update capabilities - add, delete, etc. | User ID / Passwords provide the correct update capabilities for each profile. Users are permitted to add/delete/update bases on their user profiles. | Logon using all key security profiles
Interface Testing
Execute each test script in the Interface Test Plan. | All test execute as expected in the Production region
Print Operations
1. Test printing of contracts, forms, letters and bills after an Ingenium batch cycle and subsequent Exstream batch cycle. | All key documents form the Exstream batch cycle print as expected with no format or data errors. Output is printed from the correct paper tray and prints in the prescribed sequence. | Test in Production region
2. Test printing of checks (via Exstream) after an Ingenium batch cycle. | Checks print as expected with no format or data errors. All print security features are tested successfully. | Test in Production region
3. Test printing of Ingenium reports after a batch cycle. | Ingenium batch reports print as expected with no format or data errors. | Test in Production region
4. Test Print 'Q' Manager for all printing jobs. | Print 'Q' Manager allows operators to manage print jobs from their console. Print jobs can be managed for failure scenarios, printer problems and other key operational scenarios.
5. Test the printing performance for high volume output (e.g., checks, letters, etc.) | Printing operations produce output in expected time frames with minimal delays.
TEST | TEST PARTICIPANTS | TEST COORDINATOR(S) | TESTED SYSTEMS
Performance Test | Doug Mulcahy, Tuan DoDang, Steve Wellman | Joe Taylor, Doug Mulcahy | Ingenium, Tele-Marketing, Sales Illustration
Security Test | Jay Sankoff, Jim Coady | Dee Capua | Ingenium
Batch Test | Ernie Perry, Steve Wellmann, Roland Michaud | Tuan DoDang, Brian Driscoll | Ingenium, Storage Array
Print Operations | Ernie Perry, Harold Frohlich | Joe Taylor | HP Printers, Print "Q" Manager
Failure Scenarios | Doug Mulcahy, Tuan DoDang | Steve Wellman, Joe Taylor | SunFire 6800, StorageTek Disk Array, Cybermation server
Migrations / Promotions | Steve Wellman, Doug Mulchay | Doug Mulchy | System regions - Groucho, Chico, Swordfish
Interface Test | Jay Sankoff, Brian Driscoll, Tuan DoDang, Wayne Lowry | Steve Heffner